## Cover Page
TC Energy Document Number: | 25472-101-V2A-MTNF-Z0000
Submittal Date: | 2020-12-22
Submittal Number: | 25472-101-V2A-MTNF-Z0000
PO#: | 4500337398
Applicable Tag#(s): | 22-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01
Owner: TC Energy
Name of Project: Keystone XL Pipeline Project
Project Location:
Supplier Submittal Requirements

## SSR Revision History
Revision # | Revision Date | Revision Description
01 | 2020-07-29 | Issuing for SSR Acceptance
02 | 2020-08-12 | Corrections to SSR - Reissuing for Acceptance
03 | 2020-08-25 | Corrections to SSR - Reissuing for Acceptance
04 | 2020-12-22 | Additions to SSR
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Supplier Submittal Requirements
TO BE COMPLETED BY SUPPLIER | [9 empty] | TO BE COMPLETED BY TC Energy
* PLANNED SUBMITTAL DATE | * ITEM DESCRIPTION NO. | * ITEM CATEGORY CODE | * PO MILESTONE DOCUMENT | * SUPPLIER DOCUMENT TITLE | SUPPLIER DOC NO | SUPPLIER DOC REV | EQUIPMENT NO / TAG NO | SUPPLIER REQUEST TO VOID DOC | * SUPPLIER REFORECAST SUBMITTAL DATE | TC Energy Document No | CLIENT REVIEW REQUIRED FOR THIS DOCUMENT
2020-12-01 |  | KB | No | AGI WESTEEL STRUCTURAL AND MISC STEEL QUALITY SURVEILLANCE |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0001
2020-08-12 |  | YB | No | SSR |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0000
2020-12-31 | 1 | EX | No | EHT TESTING AND INSTALLATION REPORTS |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0002
2020-12-31 | 2 | IA | No | 25016433 TABLE OF CONTENT |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0003
2020-12-31 | 3 | IB | No | MANUFACTURING RECORD BOOK & DATA BOOK |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0004
2020-12-24 | 4 | IC | No | MATERIAL CERTIFICATES | 25016433 MTRs | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0005
2020-12-24 | 5 | IE | No | CODE_STANDARD_ COMPLIANCE_CERTIFICATES | Code/Standard/Compliance Certificates | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0006
2020-12-24 | 6 | IH | No | AIR & SOAP TEST CERTIFICATE |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0007
2020-07-29 | 7 | LA | No | EQUIPMENT DATA SHEETS | 25016433 Datasheet | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0008
2020-08-19 | 8 | MA | No | EQUIPMENT DETAIL DRAWINGS | 285503HD 25016433 | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0009
2020-07-29 | 9 | MC | No | SUMP TANK FABRICATION AND FINISHING CROSS SECTIONS | 285503HD 25016433 (PRODUCTION DRAWINGS) | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0010
2020-07-29 | 10 | MC | No | STRUCTURAL SKID AND PLATFORM PLAN, ELEVATION AND SECTIONS_SUPER CEDED BY 25472- 101-V1A-MTNF- Z0032 |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0011
2020-07-29 | 11 | NA | No | WELD PROCEDURES_WP S AND PQR_AND WELD MAPS | QAP8245WI | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0012
2020-07-29 | 12 | ND | No | BLAST MEDIA / INTERNAL EXTERNAL PAINT DATA | QCF8258 / QAP8244 | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0013
2020-12-31 | 12 | ND | No | COATING RECORDS - PAINT INSPECTION | 25016433 QCF8243A (COATING RECORD) | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0014
2020-07-29 | 14 | OF | No | OPERATING & MAINTENANCE MANUALS | Operating & Maintenance Manual | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0015
2020-12-31 | 15 | QB | No | PNEUMATIC | ES15323 | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0016
2020-07-29 | 16 | WC | No | STRUCTURAL STEEL FRAMING CALCULATION C_W FOUNDATION REACTION FORCES | 25016433 HFV11000 pile reaction forces | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0017
2020-07-29 | 17 | WI | No | EHT CALCULATIONS - ELECTRICAL ZONE DRAWING FOR 285503HD TANK | 25016433 EHT calculations - electrical zone drawing for 285503hd tank | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0018
2020-07-29 | 18 | XB | No | PACKING SHIPPING HANDLING AND STORAGE AND PRESERVATION PROCEDURES | QAP7550 / QAP7561 | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0019
2020-07-29 | 19 | XE | No | 25016433 INSTALLATION INSTRUCTIONS |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0020
2020-07-29 | 20 | YA | No | INSPECTION AND TEST PLAN | Inspection Test Plan | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0021
2020-07-29 | 21 | YB | No | SUPPLIERS SCHEDULES | 25016433 Fabrication Schedule | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0022
2020-12-31 | 6 | IH | No | LIFT LUG MPI TEST REPORT | Lift lug MPI test Report REPORT | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0023
2020-12-31 | 22 | YE | No | NON CONFORMING REPORT |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0024
2020-07-29 | 14 | OF | No | OPERATIONS AND MAINTENANCE MANUAL ULC APPROVED ABOVE GROUND CONTAINED TANKS HORIZONTAL FUEL VAULT |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0025
2020-08-19 | 8 | MA | No | 25016433 ENVIRONMENTAL LOAD COMBINATIONS | 25016433 Environmental | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0026
2020-08-19 | 8 | MA | No | CENTER OF GRAVITY | 25016433 COG | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0027
2020-07-29 | 19 | XE | No | DECAL INSTALLATION INSTRUCTIONS | 272814 Decal Install | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0028
2020-07-29 | 10 | MC | No | SUMP TANK FOR REACTION DETAILS | 25016433 HFV11000 | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0029
2020-07-29 | 10 | MC | No | FULL TANK SKID ASSEMBLY & PLATFORM DRAWING |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0030
2020-12-21 | 22 | YE | No | SUPPLIER DEVIATION DISPOSITION REQUESTS (SDDRS) |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0035
2020-12-21 | N/A | YX | No | QUALITY PROCEDURES 00231.R1.SA.19.01 / QAP75004 |  | 0 | 122-LKSDE-B0-OST-01 123-MTRSP-B0-OST-01 124-OYENS-B0-OST-01 127-PIAPT-B0-OST-01 128-GRSSY-B0-OST-01 |  |  | 25472-101-V2A-MTNF-Z0036

## Instructions & Legend
LEGEND
COVER PAGE |  | Supplier to complete the TC Energy Document Number, Submittal Date, Submittal Number, PO#, and list all applicable tags
SUBMITTAL REQUIREMENTS | Columns A - J | Supplier to complete columns A-J. Columns with * are required. *Column A - PLANNED SUBMITTAL DATE: this field is used to record the calendar date that corresponds to the number of days in the Document Submittal Schedule column of Part 2 - Attachment DD of the MR (Material Requisition). *Column B - ITEM DESCRIPTION NO.: this field is used to record the number provided in the Item Description No. column of Part 2 - Attachment DD of the MR (Material Requisition). *Column C - ITEM CATEGORY CODE: this field is used to record the two letter code provided in the Document Category Code column Part 2 - Attachment DD of the MR (Material Requisition). *Column D - PO MILESTONE DOCUMENT: this field is used to indicate if the document is attached to a PO payment milestone. The details regarding payment milestones are found in PO Part 3 Commercial Requirements under the Payment Terms section. If the document is attached to a milestone this column should read Yes, and if the document is not attached to a milestone the column should read No. *Column E - SUPPLIER DOCUMENT TITLE: this field is used to record the document title for each document. Column F - SUPPLIER DOC NO: this field is used for the supplier to provide their internal document number. Column G - SUPPLIER DOC REV: this field is used for the supplier to provide their internal document revision number. Column H - EQUIPMENT NO / TAG NO: This field is used to record the equipment and tag numbers associated to the document. Column I - SUPPLIER REQUESTS TO VOID DOC: this field is used to request that an existing TC Energy Document Number be voided. The only valid reasons to void a TC Energy Document Number would be that the document is no longer a requirement and the PO Section DD has been revised to remove the requirement or if the TC Energy engineer agrees that the information is captured in another document. This field should be left blank or select VOID from dropdown if vendor is REQUESTING a void. The SSR will be formally reiewed and approved by the Lead Reviewer (LR). Document will be considered VOID once the CODE 1 stamp has been assigned. *Column J - SUPPLIER REFORECAST SUBMITTAL DATE: this field should be on or before the date provided in Column A. Column A is the contractual submittal date, this date is the date the vendor is committing to submit the document. If a date later than column A is entered that must be approved by TC Energy LR (Lead Reviewer).
| Note: | Supplier must list all planned submittals for each category and then submit this document to Encompass for Engineering approval. The SSR will be returned to the supplier with the TC Energy document numbers listed. DO NOT REMOVE any existing line items from the SSR. If there are any updates (new documentation or VOID any existing documentation) to the content of the SSR the SSR will need to be revised and reissued for CODE1 approval. Any changes needed to the existing list of documents must be approved using the SSR template.
| Columns K - L | When submitting the SSR for the first time, the Document Control team will assign TC Energy document numbers for the documents listed in the SSR. The SSR will be returned to the supplier to and will also be issued for approval in Encompass. After LR approves SSR. TC Energy Document Management creates placeholders in Encompass using these numbers. Any changes to the existing documenation listed in the approved SSR will be managed via the SSR.
SSR REVISION HISTORY |  | When any supplier completed fields of the SSR need to be revised (i.e. increasing or decreasing the number of planned submittals for a given require submittal category, etc), revise the "Submittal Requirements" tab of the SSR and track the revisons in the "SSR Revision History" tab. All revisions to the SSR must have an entry on the SSR Revision History tab and must be formally submitted via Encompass.

## Dropdown Validation (hidden)
PO Mileston Doc Table | Request to Void Table | Client Comments - Proprietary
Yes | Void | Yes
No