## Help instructions
Description
Project | This is the project name and unique identifier
PO/RO # | This is the Purchase Order # or Release Order # that the item was purchased on
Item Status to Project (Surplus, Required, Transfered) | Surplus means item will be leftover once project is complete. Required is an uninstalled item required to complete fabrication. Transfered is an item shipped
PK Tag # | The Vender Package Tag #
CWP # (If status is required) | The CWP # the item was purchased for but only if not surplus
Module # (If status is required) | The Module # within the CWP # the item was purchased for but only if not surplus
Tag # | This is the Tag # that is associated with the items datasheet or Spec. This is not the stockcode unique to the supplier.
Model # | This is the Model # that is associated with the manufacturers datasheet or Spec. This is like the stockcode unique to the supplier.
Material Category | Category of Material. EP does not need to fill out but would be helpful. Sample for PVFF include:
| Bends | Cap | Flexball | Lap Joint- Stub End | PIPE- Coated | Seal Ring | SWAGE Conc | Union
| Blind-Flange | Chain Op | Gasket- SPWD | Nipple | Pipet | Rotaball | SWAGE Ecc | VALVE
| Blind-Spectacle | Coupling | Gasket- RTJ | Orifice- Flange | Plug | SCREW | SWAGE Union | Weldolet
| Blind-Paddle | Elbolet | Graylock- Hub | Orifice- Plate | Random | Nuts | Tag'd Elec | Shipping Steel
| Blind- Hub | Elbow 45 | Graylock- Ring | Orifice- Restriction | Red Conc | Stud Bolt | Tag'd Inst. | W-Beam
| Bluesky- Hub | Elbow 90 | Graylock- Clamp | PIPE- ERW | Red ECC | Sockolet | Tee | Channel
| Bluesky- Ring | Flange | Junction Box | PIPE- SMLS | Bleed Ring | SP ITEM | Tee Red | Angle
| Bluesky- Clamp | Flange- Hub | Lap Joint- Flange | PIPE- HDPE | Retainer Ring | SS Tags | Thredolet | HSS
Size | Size of the item. Connection size or outside diameter etc. (Utilize decimals please)
Size Unit of measure | Unit of measure. (m, each, in, Ring No. etc)
Rating | # (Lbs) Rating for PVFF. Sample include:
| 150 | 800 | 2000
| 300 | 900 | 3000
| 600 | 1500 | 6000
Connection Type | Type of connection for PVFF. Sample include:
| RF WN | RF SW | RTJ (RTJ WN) | BW (Bevel) | TOE (THD One end) | POE/TOE | BWxTHD
| RF | THD (Both ends) | SWxTHD | SW (Plain) | PBE (Plain One End) | BWxSW
Schedule | Scheduel of the material. If it’s an engineered calculated wall thickness record WT in mm. Sample include:
| Sch 20 | Sch 80 | Sch 160/XXS | Sch STD/XS | Sch 120x80
| Sch 40 | Sch 100 | Sch 100/160 | # mm | Sch 10
| STD | Sch 120 | Sch 160/80 | Sch 80/160
| Sch 60 | Sch 160 | Sch 120/160 | Sch 80/XXS
| XS (XH) | XXS (XXH) | Sch 120/XS | Sch 10/80
Material Code | Code Material is designed to. Sample includes:
| A105-N | A252 | A350 | A516 | A216 | A815
| A106 | A312 | A182 | A790 | A194 | A403
| A234 | A333 Gr. B | A420 | Z245 | A266 | API 5L
Material Grade/UNS | Material Grade. Sample include:
| Gr 290 | Gr 483 | F51 | WPL6 | Gr. B | WCC | Gr. 70 | 52 PSL 2
| 316 (SS) | Gr 550 | F53 | WPB | LF2 | Gr. 3 | SS
| Gr 448 | Gr 359 | Gr 359 (SS) | WCB | DSS (S31803/S32205) | 316L | F51 (SS)
Description | As per the EP material management system
Quantity | Amount in this line item
Quantity Unit of Measure | Unit to measure amount in this line item
| Each | Inch (in)
Meter (m)
Supplier | Who supplied the item
Current Location | Where is this item currently located. If it is going to be moving record the final destination if the EP is responsble for transportation.
Value PER item ($) | $/quantity
Total Value ($) | Total value of PO line item
Original/ Modified | Original means purchased is a shelf item. Modified means it is not equivalent to a shelf item but was Engineered/Modified after sale.
Comments | Any notes please write here

## Project Procurement List
Definition |  |  |  | Definition |  |  |  | Definition |  |  |  | Definition |  |  | Definition
All mechanical material that was a bulk purchase. |  |  |  | All Mechanical Equipment, is Assembled or purchased at a package level. (Except Valves, E&I) |  |  |  | All Electrical and Instrumentation material |  |  |  | All Bulk Structural Steel in Storage |  |  | All Piles currently not installed
PVFF + Other | Material Management by: |  |  | Equipment, Packages & Modules | Material Management by: |  |  | E&I | Material Management by: |  |  | Structural Steel | Material Management by: |  | Piles | Material Management by:
Material Category | EP | CMT | SCM | Material Category | EP | CMT | SCM | Material Category | EP | CMT | SCM | Material Category | EP | CMT | Material Category | EP | CMT
Bends | Yes |  |  | Battery | Yes |  |  | AAH-Alarm Horn | Yes |  |  | Various Sizes of Steel | Yes |  | Various Sizes of Piles | Yes | Yes
Blind-Flange | Yes |  |  | Blower | Yes |  |  | AE-Analyzer Element | Yes |  |  | Shipping Beams |  | Yes
Blind-Spectacle | Yes |  |  | Building |  |  | Yes | AIT-Analysis Indicating Transmitter | Yes
Blind-Paddle | Yes |  |  | Centrifuge | Yes |  |  | ALH-Beacon | Yes
Blind- Hub | Yes |  |  | Combustion | Yes |  |  | BT-Burner Transmitter | Yes
Bluesky- Hub | Yes |  |  | Compressor | Yes |  |  | Cable | Yes
Bluesky- Ring | Yes |  |  | Coolers | Yes |  |  | DCS Equipment | Yes
Bluesky- Clamp | Yes |  |  | Drives | Yes |  |  | Display | Yes
Cap | Yes |  |  | Ejectors | Yes |  |  | Enclosure | Yes
Chain Op | Yes |  |  | Exchanger | Yes |  |  | FE- Flow Element | Yes
Coupling | Yes |  |  | Equipment Module (EQM) | Yes | Yes |  | FG-Sight Glass | Yes
Elbolet | Yes |  |  | Filer | Yes |  |  | FIT-Flow Indicating Transmitter | Yes
Elbow 45 | Yes |  |  | Filter | Yes |  |  | FO-Flow Orifice | Yes
Elbow 90 | Yes |  |  | Generator | Yes |  |  | Fuse | Yes
Flange | Yes |  |  | Mixer | Yes |  |  | Junction Box | Yes
Flange- Hub | Yes |  |  | Motor | Yes |  |  | LAH-Level Alarm High | Yes
Flexball | Yes |  |  | Motor Control Center | Yes |  |  | LAL-Level Alarm Low | Yes
Gasket- SPWD | Yes |  |  | OTSG |  |  | Yes | LG-Level Gauge | Yes
Gasket- RTJ | Yes |  |  | Packaged Equipment (PK) | Yes |  |  | LI-Local Indicator Level | Yes
Graylock- Hub | Yes |  |  | Pipe | Yes |  |  | LIT-Level Indicating Transmitter | Yes
Graylock- Ring | Yes |  |  | Pipe Rack Module (PRM) | Yes | Yes |  | LLH- Beacon | Yes
Graylock- Clamp | Yes |  |  | Pump | Yes |  |  | LSH-Level Switch High | Yes
Lap Joint- Flange | Yes |  |  | Sump | Yes |  |  | Media Converter | Yes
Lap Joint- Stub End | Yes |  |  | Tank |  |  | Yes | PDIT-Pressure Differential Indicating Transmitter | Yes
Nipple | Yes |  |  | Vessel | Yes |  |  | PG-Pressure Gauge | Yes
Orifice- Flange | Yes | [6 empty] | PIT-Pressure Indicating Transmitter | Yes
Orifice- Plate | Yes | [6 empty] | Pressure sensing string | Yes
Orifice- Restriction | Yes | [6 empty] | Pressure Switch | Yes
PIPE- ERW | Yes | [6 empty] | Probe | Yes
PIPE- SMLS | Yes | [6 empty] | PS- Pressure Switches | Yes
PIPE- HDPE | Yes | [6 empty] | Resistor | Yes
PIPE- Coated | Yes | [6 empty] | RO-Restriction Orifice | Yes
Plug | Yes | [6 empty] | RTD-Resistance Temperature Detector | Yes
Red Conc | Yes | [6 empty] | SSS Processor | Yes
Red ECC | Yes | [6 empty] | TCV-Temperature Control Valve | Yes
Bleed Ring | Yes | [6 empty] | Termination Kit | Yes
Retainer Ring | Yes | [6 empty] | TE-Temperature Element | Yes
Seal Ring | Yes | [6 empty] | TG-Temperature Gauge | Yes
Rotaball | Yes | [6 empty] | Thermostat | Yes
Screw | Yes | [6 empty] | TIT-Temperature Indicating Transmitter | Yes
Nuts | Yes | [6 empty] | Transformer | Yes
Stud Bolt | Yes | [6 empty] | TW-Thermowell | Yes
Sockolet | Yes | [6 empty] | UPS | Yes
SP ITEM | Yes | [6 empty] | UTP | Yes
SS Tags | Yes | [6 empty] | VFD | Yes
SWAGE Conc | Yes
SWAGE Ecc | Yes
SWAGE Union | Yes
Tee | Yes
Tee Red | Yes
Threadolet | Yes
Union | Yes
Valve- Manual | Yes | Yes
Valve- Control | Yes | Yes
Weldolet | Yes

## 1) PVFF + Other
| PVFF + Other Tracker |  |  |  | Legend
Nice to have
| Material List for: | Pipe |  |  |  | Required
Valves
Flanges
Fittings
| Project Number | PO/RO # | PO Year | Item Status to Project (Surplus/Req'd/Trans) | CWP # (If status is required) | Module # (If status is required) | Material Category | Tag # | Size | Size Unit of measure | Rating | Connection Type | Schedule | Material Code | Material Grade/UNS | Description (as Purchased) | Quantity | Quantity Unit of Measure | Supplier | Current Location | Value PER item ($) | Total line Value ($) | Original/ Modified | Comments
Example | CNV014 | EJD-1988-QWERTY | 2012 | Surplus |  |  | VALVE | 0.5_GS-08S00 | 0.5 | in | 900 | SW |  | A359 |  | 1/2 VALVE GATE SW CS NACE 900LB A359 | 53 | EA | MRC | MTE Logistix | 92.34 | 4894.02 | ORIGINAL
Example | CNV014 | EJD-1960-QWERTY | 2013 | Required | G02.150.1.05 | 03A | FLANGE |  | 10X3/4 | in |  | RF | XH | A105N | SS 316 | 10X3/4 CL 300 RED S/W FLANGE RF XH BORE A105N SS316 | 10 | EA | Trans AM | Tundra Process Solutions | 1265.7 | 12657 | ORIGINAL
Example | CNV014 | EJD-1560-QWERTY | 2013 | Surplus |  |  | Blind |  | 2 | in | 150 | RF |  | A/SA 182 | F51 | 2" NPS 150# RF BLIND FLANGE A/SA 182 F51 | 10 | EA | Trans AM | LaCorey | 1265.7 | 12657 | ORIGINAL
Example | CNV014 | EJD-1560-QWERTY | 2015 | Required | G02.150.1.05 | 03A | FLANGE |  | 8 | in | 600 | RF WN | 8.2mm | Z245.12 | Gr 448 Cat 1 | 8" NPS 600# RF WN FLANGE 8.2MM Z245.12 GR 448 CAT 1 | 10 | EA | Trans AM | Foster Creek Warehouse | 1265.7 | 12657 | ORIGINAL
Example | CNV014 | EJD-1981-QWERTY | 2015 | Required | G02.150.1.05 | 03A | PIPE |  | 20 | in |  |  | STD | A106B | SMLS | M-20 PIPE A106B STD BLK SMLS BE DRL | 6 | m | Westlund | WESTLUND | 474.26 | 474.26 | ORIGINAL

## 2) Equip, Mods & PK
Equipment, Fabricated Packages and Modules
Material List for: | Tags with PK-
Tags with EQM and PRM
Equipment with Tags
Project Number | PO/RO # | PO Year | Item Status to Project (Surplus/Req'd/Trans) | PK Tag # | CWP # (If status is required) | Module # (If status is Assembled) | Tag # | Description (as Purchased) | Quantity | Quantity Unit of Measure | Supplier | Current Location | Value PER item ($) | Total line Value ($) | O,S&D Form? | Comments
2016-012 | AFE 16165217 | 2016 | Surplus |  |  |  | W06-V-9220 | Propane Storage Bullet | 1 | EA | Bilton Welding & Manufacturing LTD | FC W06 pad | 215906.25 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016 | Surplus | PK-9210 |  |  | PK-9210 | Propane offloading skid | 1 | EA | Pillar Fabricators | FC W06 pad | 68810.81 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016 | Surplus | PK-9250 |  |  | PK-9250 | Propane pump skid | 1 | EA | Pillar Fabricators | FC W06 pad | 332495.45 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016 | Surplus |  |  |  | W06-P-9230A/B | P-9230 A/B booster pumps | 1 | EA | EC & M Electric | FC W06 pad | 90216 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016 | Surplus |  |  |  | W06-P-9240A/B | P-9240 A/B feed pumps | 1 | EA | West Power | FC W06 pad | 149215.5 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016 | Surplus |  |  |  | W06 VFD-9240A/B | VFD & soft start enclosures | 1 | EA | Simark Controls | FC W06 pad | 29619.45 |  |  | MOC 18089 decommissioned in place
2016-012 |  | 2016

## 3) E & I
Electrical Items and Instrumentation
Legend
| Material List for: | Electrical Heat Trace |  |  |  |  | Nice to have
|  | Juction Boxes |  |  |  |  | Required
Instrumentation (FE, PG…)
Cable
| Project Number | PO/RO # | PO Year | Item Status to Project (Surplus/Req'd/Trans) | PK Tag # | CWP # (If status is required) | Module # (If status is required) | Tag # | Model # | Material Category | Description (as Purchased) | Quantity | Quantity Unit of Measure | Supplier | Current Location | Value PER item ($) | Total line Value ($) | O,S&D Form? | Comments
Example | CNV014 | EJD-1988-QWERTY | 2012 | Surplus | PK-53 |  |  | E15-HVJBs |  | Junction Box | 5kV Junction Box | 1 | EA | EECOL | LaCorey | 920562.34 | 920562.34 | No
Example | CNV015 | EJD-1988-QWERTY | 2013 | Surplus |  | H03.303.3.03 | 1A | UPS-0303A |  | UPS | The supply of a 15kVA UPS c/w rectifier/charger, inverter and static transfer switch. | 12 | EA | Spartan Controls | Foster Creek | 920562.34 | 920562.34 | No
Example | CNV014 | EJD-1981-QWERTY | 2015 | Required |  | C05.506.3.02 | 6B | 05-LIT-5870 |  | Instrument | LIT-Level Indicating Transmitter | 1 | EA | Honeywell | Installed |  |  | No

## 4) Structural Steel
Structural Steel
| Material List for: | W-Beam, C-Beam…Ect
Shipping Steel
Plate…Ect
| Project Number | PO/RO # | PO Year | Material Category | Member Section | Imperial Sizes | Description (as Purchased) | Quantity | Quantity Unit of Measure | Supplier | Current Location | Value PER item ($) | Total line Value ($) | Original/ Modified | Comments
Example | CNV014 | EJD-1988-QWERTY | 2012 | W-Beam | W460x74x 20 ft. | W18X50 | Structural Steel | 53 | EA | NWL | NWL | 92.34 | 4894.02 | ORIGINAL
Example | CNV014 | EJD-1960-QWERTY | 2013 | W-Beam | W360x162x 60 ft. | W14X109 | Structural Steel | 10 | EA | NWL | NWL | 1265.7 | 12657 | ORIGINAL
Example | CNV015 | EJD-1960-QWERTY | 2013 | Shipping Beam | 18m |  | Shipping Beam for 18m length module |  |  | NWL | Nisku Module Yard |  |  | MODIFIED
Example | CNV014 | EJD-1560-QWERTY | 2015 | W-Beam | W360x134x 60 ft. | W14X90 | Structural Steel | 10 | EA | NWL | NWL | 1265.7 | 12657 | ORIGINAL
Example | CNV014 | EJD-1560-QWERTY | 2015 | W-Beam | W360x91x 20 ft. | W14X61 | Structural Steel | 10 | EA | NWL | NWL | 1265.7 | 12657 | ORIGINAL
Example | CNV014 | EJD-1981-QWERTY | 2015 | W-Beam | W360x45x 20 ft. | W14X30 | Structural Steel | 6 | EA | NWL | NWL | 474.26 | 474.26 | ORIGINAL
|  |  |  | W-Beam | W310x129x 60 ft. | W12X87
|  |  |  | W-Beam | W310x118x 60 ft. | W12X79
|  |  |  | W-Beam | W310x97x 60 ft. | W12X65
|  |  |  | W-Beam | W310x79x 60 ft. | W12X53
|  |  |  | W-Beam | W310x67x 20 ft. | W12X45
|  |  |  | W-Beam | W310x60x 60 ft. | W12X40
|  |  |  | W-Beam | W310x39x 20 ft. | W12X26
|  |  |  | W-Beam | W250x89x 60 ft. | W10X60
|  |  |  | W-Beam | W250x73x 60 ft. | W10X49
|  |  |  | W-Beam | W250x67x 60 ft. | W10X45
|  |  |  | W-Beam | W250x58x 60 ft. | W10X39
|  |  |  | W-Beam | W250x49x 60 ft. | W10X33
|  |  |  | W-Beam | W250x45x 30 ft. | W10X30
|  |  |  | W-Beam | W200x46x 60 ft. | W8X31
|  |  |  | W-Beam | W200x36x 60 ft. | W8X24
|  |  |  | W-Beam | W200x27x 60 ft. | W8X18
|  |  |  | W-Beam | W150x22x 40 ft. | W6X15
|  |  |  | WT-Beam | WT125x65.5x 20 ft. | WT5X44
|  |  |  | WT-Beam | WT155x59x 20 ft. | WT6X39.5
|  |  |  | WT-Beam | WT155x48.5x 20 ft. | WT6X32.5
|  |  |  | WT-Beam | WT155x39.5x 20 ft. | WT6X26
|  |  |  | WT-Beam | WT155x30x 20 ft. | WT6X20
|  |  |  | WT-Beam | WT125x24.5x 60 ft. | WT5X16
|  |  |  | WT-Beam | WT125x19.5x 20 ft. | WT5X13
|  |  |  | WT-Beam | WT75x15x 20 ft. | WT3X10
|  |  |  | WT-Beam | WT100x7.5x 20 ft. | WT4X5
|  |  |  | HSS | HSS152x152x13x 20 ft. | HSS6X6X1/2
|  |  |  | Angle | L152x152x19x 60 ft. | L6X6X3/4
|  |  |  | Angle | L152x102x19x 60 ft. | L6X4X3/4
|  |  |  | Angle | L152x102x16x 60 ft. | L6X4X5/8
|  |  |  | Angle | L127x127x13x 20 ft. | L5X5X1/2
|  |  |  | Angle | L127x89x16x 60 ft. | L5X3.5X5/8
|  |  |  | Angle | L127x89x13x 60 ft. | L5X3.5X1/2
|  |  |  | Angle | L127x76x7.5x 40 ft. | L5X3X5/16
|  |  |  | Angle | L127x76x6.4x 20 ft. | L5X3X1/4
|  |  |  | Angle | L102x102x9.5x 20 ft. | L4X4X3/8
|  |  |  | Angle | L102x102x7.9x 60 ft. | L4X4X5/16
|  |  |  | Angle | L102x76x13x 20 ft. | L4X3X1/2
|  |  |  | Angle | L102x76x9.5x 60 ft. | L4X3X3/8
|  |  |  | Angle | L102x76x7.9x 20 ft. | L4X3X5/16
|  |  |  | Angle | L76x76x9.5x 40 ft. | L3X3X3/8
|  |  |  | Angle | L76x76x7.9x 40 ft. | L3X3X5/16
|  |  |  | Angle | L76x76x6.4x 40 ft. | L3X3X1/4
|  |  |  | Angle | L51x51x6.4x 40 ft. | L2X2X1/4
|  |  |  | Channel | C250x23x 60 ft. | C10X15
|  |  |  | Channel | C230x20x 20 ft. | C9X13
|  |  |  | Channel | C200x21x 40 ft. | C8X13
|  |  |  | Channel | C200x17x 60 ft. | C8X11
|  |  |  | Channel | C150x12x 20 ft. | C6X8
|  |  |  | Channel | C100x8x 40 ft. | C4X5
|  |  |  | Channel | C75x9x 60 ft. | C3X6

## 5) Piles
| Pile Tracker | [30 empty] | 7788.96
| Material List For: | Piles
To be filled out by requester
[8 empty] | Wall T. (mm) | 7.11 |  |  |  | 8.18 |  |  |  | 9.27 |  |  |  | 9.53 |  |  |  | 9.53
[8 empty] | Pile Dia.(mm) | 168 |  |  |  | 219 |  |  |  | 273 |  |  |  | 324 |  |  |  | 406 |  |  |  | 457
| To be filled out by Cenovus | [6 empty] | Dia in. | 6" |  |  |  | 8" |  |  |  | 10" |  |  |  | 12" |  |  |  | 16" |  |  |  | 18" |  | To be filled out by Cenovus
Surplus List Item # | Project Number | PO/RO # | PO Year | Item Status to Project (Surplus/Req'd/Trans) | Material Verification Date | Contact at Location | Laydown Location | Length (m) | 12 | 15 | 18 | 20 | 12 | 15 | 18 | 20 | 12 | 15 | 18 | 20 | 12 | 15 | 18 | 20 | 12 | 15 | 18 | 20 | 12 | 20 | $/Pile | Total Value ($) | Comments & MTR #'s
Example | CNV014 | EJD-1988-QWERTY | 2012 | Surplus | 2015-12-03 | Elwin Ash | FC- BP-11 | Quantity | [6 empty] | 0 | [15 empty] | 747.9 | 0
Example | CNV014 | EJD-1988-QWERTY | 2015 | Surplus | 2015-12-03 | Elwin Ash | FC- BP-11 | Quantity |  |  | 6 | [19 empty] | 1298.16 | 7788.96 | SCM-MTR-010(6)
Quantity
Quantity
Quantity

## 6) Common Service
Common Service
| Material List for: | Trailers
Furniture
Rig Mat
Jersey Barrier
| Project Number | PO/RO # | PO Year | Item Status to Project (Surplus/Req'd/Trans) | Material Category | Size | Size Unit of measure | Rating | Description (as Purchased) | Quantity | Quantity Unit of Measure | Supplier | Current Location | Value PER item ($) | Total line Value ($) | Original/ Modified | Comments
Example | CNV014 | EJD-1988-QWERTY | 2012 | Surplus | Trailer | 8x60 | ft |  | 8' x 60' BOXX Modular Lunch Trailer | 1 | EA | BOXX Modular | Foster Creek | 65400 | 65400 | ORIGINAL
Example | CNV014 | EJD-1960-QWERTY | 2013 | Surplus | Trailer | 12x60 | ft |  | 12' x 60' Locker Trailer | 12 | EA | BOXX Modular | La Corey | 98100 | 1177200 | ORIGINAL
Example | CNV014 | EJD-1560-QWERTY | 2013 | Surplus | Furniture | 29x70 | in |  | Electric Height Adjustable Table | 2 | EA | Teknion | CSS | 415 | 830 | ORIGINAL
Example | CNV014 | EJD-1560-QWERTY | 2015 | Surplus | Appliance |  |  |  | Refridgerator | 11 | EA | N/A | Nisku Module Yard | 1265.7 | 13922.7 | ORIGINAL
Example | CNV014 | EJD-1981-QWERTY | 2015 | Surplus | Storage |  |  |  | Greenlee Boxes | 9 | EA | Greenlee | Nisku Module Yard | 649 | 5841 | ORIGINAL